## Slide 1: AsiaCrypt 2003- Program Committee Report
Chi Sung Laih
Nov.30~Dec.4,2003
Taipei, Taiwan

## Slide 2: Preparations for Asiacrypt 2003
Dec.15,2002: AC’03 website was online.
Jan.17,2003: AC’03 logo was designed.
March 15: Online submission was up and running.
May 22: Deadline for submission
May 26: Review to start
July 13: All review reports were received.
July 15~29: Discussion among PC members
August 1: Send notifications to authors
August 17: registration started
Sep.20: The final version of proceedings was sent to Springer-Verlag.

## Slide 3: Program Committee Members

## Slide 4: Submissions
188 submissions (26 countries)
32 accepted (15 countries)
One of 32 papers was merged
17 % acceptance rate

## Slide 5: Submissions by Continent
Asia- 108
America- 27
Europe- 53

## Slide 6: Submissions by Country (Total:26)
Australia-10
China-17
Hong Kong-4
India-10
Japan-23
Korea-23
Malaysia-1
Singapore-4
Taiwan-15
Canada-2
USA-27
Bangladesh-1
Belgium-2
Brazil-1
Denmark-2
Finland-4
France-16
Germany-7
Iran-1
Israel-3
Macedonia-1
Poland-1
Sweden-1
Switzerland-9
UK-2
Yugoslavia-1

## Slide 7: Accepted Papers from 15 countries

## Slide 8: Reviews
27 reviewers from 17 countries
All submissions and reviewing process were anonymous.
Each paper was reviewed by at least 3 pc members.
Papers submitted by one of the pc members were reviewed by 6 members.
133 external reviewers

## Slide 9: Revisions
Out of 188 submissions, 45 had revisions.
21 papers were revised 1 time
7 papers were revised 2 times
9 papers were revised 3 times
1 paper was revised 4 times
2 papers were revised 5 times
1 paper was revised 6 times
1 paper was revised 7 times
3 papers were revised 9 times

## Slide 10
~Thank You~
Chi Sung Laih